## Sheet1
Week | Frontend | Backend
2021-02-02 | build system | build system
2021-02-09 | Test continous delivery | Test continuous delivery
2021-02-16 | API that returns no data | Connects to an API
2021-02-23 | Configure GitHub Actions | Enable GitHub Actions
2021-03-02 | Run remote tests and verify | Replace yml code with scaffolding
2021-03-09 | Continuous Delivery on Azure | Get the Flask starter code & add to project
2021-03-16 | Set up Azure Pipelines | Configure App Service permissions
2021-03-23 | Perform prediction run against a working deployed Azure Application | Make predictions and make necessary changes
2021-03-30
2021-04-06 | Backend ready for QA | Frontend ready for QA
2021-04-13
2021-04-20
| Goals | Goals
| ML API | Deployed on Azure
| loggging | Flask